## aps_activity
project_id | activity_id | sequence | activity_code | activity_name | activity_type | start_time | end_time | parent_activity_id | parent_activity_name | proceeding_activity_id | proceeding_activity_name | durance | schedule_type | start_type | ms_time | resource_type | resource_id | resource_name | enable_flag | remark | create_time | create_by | update_by | update_time | attribute1 | attribute2 | attribute3 | attribute4 | attribute5 | attribute6 | attribute7 | attribute8 | attribute9 | attribute10 | attribute11 | attribute12 | attribute13 | attribute14 | attribute15
10 | 1906 | 1 | CIMP935 | 合同 | REVIEW | 2024-10-15 | 2024-10-19 |  |  |  |  | 5 | SP |  |  | PROD_LINE | 33 | 评审组 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1907 | 2 | CIMP936 | 设计A | DESIGN | 2024-10-21 | 2024-11-06 | 1914 | 设计 |  |  | 17 | SP |  |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
10 | 1908 | 3 | CIMP937 | 设计A-1 | DESIGN | 2024-10-21 | 2024-10-25 | 1907 | 设计A | 1906 | 合同 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1909 | 4 | CIMP938 | 设计A-2 | DESIGN | 2024-10-26 | 2024-10-31 | 1907 | 设计A | 1908 | 设计A-1 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1910 | 5 | CIMP939 | 设计A-3 | DESIGN | 2024-11-01 | 2024-11-06 | 1907 | 设计A | 1909 | 设计A-2 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1911 | 6 | CIMP940 | 设计B | DESIGN | 2024-10-26 | 2024-11-06 | 1914 | 设计 |  |  | 12 | SP |  |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
10 | 1912 | 7 | CIMP941 | 设计B-1 | DESIGN | 2024-10-26 | 2024-10-31 | 1911 | 设计B | 1908 | 设计A-1 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1913 | 8 | CIMP942 | 设计B-2 | DESIGN | 2024-11-01 | 2024-11-06 | 1911 | 设计B | 1909 | 设计A-2 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1914 | 6 | CIMP943 | 设计 | DESIGN | 2024-10-21 | 2024-11-12 |  |  |  |  | 23 | SP |  |  | AREA | 17 | 设计部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
10 | 1915 | 10 | CIMP944 | 设计C | DESIGN | 2024-11-07 | 2024-11-12 | 1914 | 设计 | 1910 | 设计A-3 | 5 | SP | FS |  | PROD_LINE | 29 | 压缩机室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1916 | 7 | CIMP945 | 生产 | MAKE | 2024-11-28 | 2024-12-09 |  |  |  |  | 12 | DP |  |  | AREA | 14 | 容器车间 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
10 | 1917 | 12 | CIMP946 | 采购 | PURCHASE | 2024-11-22 | 2024-11-30 |  |  |  |  | 9 | DP |  |  | AREA | 14 | 容器车间 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
10 | 1918 | 13 | CIMP947 | 生产部件 | MAKE | 2024-11-28 | 2024-12-03 | 1916 | 生产 | 1920 | 采购部件 | 5 | DP | FS |  | AREA | 15 | 重载车间 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1919 | 14 | CIMP948 | 生产机组 | MAKE | 2024-12-04 | 2024-12-09 | 1916 | 生产 | 1918 | 生产部件 | 5 | DP | FS |  | AREA | 19 | 采购部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1920 | 15 | CIMP949 | 采购部件 | PURCHASE | 2024-11-22 | 2024-11-27 | 1917 | 采购 | 1923 | 合同生效 | 5 | DP | FS |  | AREA | 18 | 采购部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1921 | 16 | CIMP950 | 采购其他 | PURCHASE | 2024-11-26 | 2024-11-30 | 1917 | 采购 | 1923 | 合同生效 | 5 | DP | FS |  | AREA | 18 | 采购部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1922 | 13 | CIMP951 | 发运 | REVIEW | 2024-12-10 | 2024-12-14 |  |  | 1919 | 生产机组 | 5 | DP | FS |  | PROD_LINE | 21 | 工艺机装配线 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
10 | 1923 | 17 | CIMP952 | 合同生效 | MAKE | 2024-11-13 | 2024-11-13 |  |  | 1915 | 设计C | 1 | SP | FS |  | AREA | 19 | 生产部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1924 | 2 | CS001126 | 合同 | REVIEW | 2024-10-23 | 2024-10-27 |  |  |  |  | 5 | SP |  |  | PROD_LINE | 33 | 评审组 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1925 | 2 | CS001127 | 设计A | DESIGN | 2024-10-28 | 2024-11-11 | 1932 | 设计 |  |  | 15 | SP |  |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
12 | 1926 | 3 | CS001128 | 设计A-1 | DESIGN | 2024-10-28 | 2024-11-01 | 1925 | 设计A | 1924 | 合同 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1927 | 4 | CS001129 | 设计A-2 | DESIGN | 2024-11-02 | 2024-11-06 | 1925 | 设计A | 1926 | 设计A-1 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1928 | 5 | CS001130 | 设计A-3 | DESIGN | 2024-11-07 | 2024-11-11 | 1925 | 设计A | 1927 | 设计A-2 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1929 | 6 | CS001131 | 设计B | DESIGN | 2024-11-02 | 2024-11-11 | 1932 | 设计 |  |  | 10 | SP |  |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
12 | 1930 | 7 | CS001132 | 设计B-1 | DESIGN | 2024-11-02 | 2024-11-06 | 1929 | 设计B | 1926 | 设计A-1 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1931 | 8 | CS001133 | 设计B-2 | DESIGN | 2024-11-07 | 2024-11-11 | 1929 | 设计B | 1927 | 设计A-2 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1932 | 5 | CS001134 | 设计 | DESIGN | 2024-10-28 | 2024-11-16 |  |  |  |  | 20 | SP |  |  | AREA | 17 | 设计部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
12 | 1933 | 10 | CS001135 | 设计C | DESIGN | 2024-11-12 | 2024-11-16 | 1932 | 设计 | 1928 | 设计A-3 | 5 | SP | FS |  | PROD_LINE | 29 | 压缩机室 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1934 | 8 | CS001136 | 生产 | MAKE | 2024-12-16 | 2024-12-25 |  |  |  |  | 10 | DP |  |  | AREA | 14 | 容器车间 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
12 | 1935 | 11 | CS001137 | 采购 | PURCHASE | 2024-12-11 | 2024-12-15 |  |  |  |  | 5 | DP |  |  | AREA | 14 | 容器车间 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW | Y
12 | 1936 | 13 | CS001138 | 生产部件 | MAKE | 2024-12-16 | 2024-12-20 | 1934 | 生产 | 1938 | 采购部件 | 5 | DP | FS |  | AREA | 15 | 重载车间 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1937 | 14 | CS001139 | 生产机组 | MAKE | 2024-12-21 | 2024-12-25 | 1934 | 生产 | 1936 | 生产部件 | 5 | DP | FS |  | AREA | 19 | 采购部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1938 | 15 | CS001140 | 采购部件 | PURCHASE | 2024-12-11 | 2024-12-15 | 1935 | 采购 | 1941 | 合同生效 | 5 | DP | FS |  | AREA | 18 | 采购部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1939 | 16 | CS001141 | 采购其他 | PURCHASE | 2024-12-11 | 2024-12-15 | 1935 | 采购 | 1941 | 合同生效 | 5 | DP | FS |  | AREA | 18 | 采购部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1940 | 14 | CS001142 | 发运 | REVIEW | 2024-12-26 | 2024-12-30 |  |  | 1937 | 生产机组 | 5 | DP | FS |  | PROD_LINE | 21 | 工艺机装配线 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
12 | 1941 | 16 | CS001143 | 合同生效 | MAKE | 2024-11-17 | 2024-11-17 |  |  | 1933 | 设计C | 1 | SP | FS |  | AREA | 19 | 生产部 | Y |  | 2024-10-29 13:17 | admin | admin | 2024-10-29 13:17 | NEW |  |  | 0
11 | 1942 | 18 | ProdLine01140 | 合同 | REVIEW | 2024-10-21 | 2024-10-25 |  |  |  |  | 5 | SP |  |  | PROD_LINE | 33 | 评审组 | Y | 2121 | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1943 | 2 | ProdLine01141 | 设计A | DESIGN | 2024-10-29 | 2024-11-14 | 1950 | 设计 |  |  | 17 | SP |  |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW | Y
11 | 1944 | 3 | ProdLine01142 | 设计A-1 | DESIGN | 2024-10-29 | 2024-11-02 | 1943 | 设计A | 1942 | 合同 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1945 | 4 | ProdLine01143 | 设计A-2 | DESIGN | 2024-11-04 | 2024-11-08 | 1943 | 设计A | 1944 | 设计A-1 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1946 | 5 | ProdLine01144 | 设计A-3 | DESIGN | 2024-11-09 | 2024-11-14 | 1943 | 设计A | 1945 | 设计A-2 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1947 | 6 | ProdLine01145 | 设计B | DESIGN | 2024-11-05 | 2024-11-14 | 1950 | 设计 |  |  | 10 | SP |  |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW | Y
11 | 1948 | 7 | ProdLine01146 | 设计B-1 | DESIGN | 2024-11-05 | 2024-11-09 | 1947 | 设计B | 1944 | 设计A-1 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1949 | 8 | ProdLine01147 | 设计B-2 | DESIGN | 2024-11-09 | 2024-11-14 | 1947 | 设计B | 1945 | 设计A-2 | 5 | SP | FS |  | PROD_LINE | 28 | 机组室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1950 | 4 | ProdLine01148 | 设计 | WORKING | 2024-10-29 | 2024-11-20 |  |  |  |  | 23 | SP |  |  | AREA | 17 | 设计部 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW | Y
11 | 1951 | 10 | ProdLine01149 | 设计C | DESIGN | 2024-11-15 | 2024-11-20 | 1950 | 设计 | 1946 | 设计A-3 | 5 | SP | FS |  | PROD_LINE | 29 | 压缩机室 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1952 | 9 | ProdLine01150 | 生产 | MAKE | 2024-12-14 | 2024-12-25 |  |  |  |  | 12 | DP |  |  | AREA | 14 | 容器车间 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW | Y
11 | 1953 | 10 | ProdLine01151 | 采购 | PURCHASE | 2024-12-09 | 2024-12-17 |  |  |  |  | 9 | DP |  |  | AREA | 14 | 容器车间 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW | Y
11 | 1954 | 13 | ProdLine01152 | 生产部件 | MAKE | 2024-12-14 | 2024-12-19 | 1952 | 生产 | 1956 | 采购部件 | 5 | DP | FS |  | AREA | 15 | 重载车间 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1955 | 14 | ProdLine01153 | 生产机组 | MAKE | 2024-12-20 | 2024-12-25 | 1952 | 生产 | 1954 | 生产部件 | 5 | DP | FS |  | AREA | 19 | 采购部 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1956 | 15 | ProdLine01154 | 采购部件 | PURCHASE | 2024-12-09 | 2024-12-13 | 1953 | 采购 | 1959 | 合同生效 | 5 | DP | FS |  | AREA | 18 | 采购部 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1957 | 16 | ProdLine01155 | 采购其他 | PURCHASE | 2024-12-12 | 2024-12-17 | 1953 | 采购 | 1959 | 合同生效 | 5 | DP | FS |  | AREA | 18 | 采购部 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-11-01 16:09 | NEW |  |  | 0
11 | 1958 | 19 | ProdLine01156 | 发运 | REVIEW | 2024-12-26 | 2024-12-31 |  |  | 1955 | 生产机组 | 5 | DP | FS |  | PROD_LINE | 21 | 工艺机装配线 | Y | 2121 | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
11 | 1959 | 15 | ProdLine01157 | 合同生效 | MAKE | 2024-11-21 | 2024-11-21 |  |  | 1951 | 设计C | 1 | SP | FS |  | AREA | 19 | 生产部 | Y |  | 2024-10-30 08:50 | admin | admin | 2024-10-30 08:50 | NEW |  |  | 0
23 | 1960 | 3 | P102431-0016001 | 1-1测试物料1发运活动 | TRANS | 2024-10-31 | 2024-09-14 |  |  |  |  | -47 | DP |  |  | PROD_LINE | 33 | 发运单元 | Y |  | 2024-10-31 14:52 | admin | admin | 2024-10-31 14:52 | NEW | N | Y | 2
29 | 1961 | 1 | P112407-0004001 | SO2024102201-SO2024102201-014包装箱发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  |  |  | 12 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -14
29 | 1962 | 2 | P112407-0004002 | SO2024102201-SO2024102201-015扎带标识牌48X28.8-147.5发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1961 |  | 13 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -15
29 | 1963 | 3 | P112407-0004003 | SO2024102201-SO2024102201-013LG32/40(配套）辅料包发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1962 |  | 13 | DP |  |  | PROD_LINE | 17 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -13
29 | 1964 | 4 | P112407-0004004 | SO2024102201-SO2024102201-010安装板发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  |  |  | 13 | DP |  |  | PROD_LINE | 17 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -10
29 | 1965 | 5 | P112407-0004005 | SO2024102201-SO2024102201-011安装板发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1964 |  | 13 | DP |  |  | PROD_LINE | 29 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -11
29 | 1966 | 6 | P112407-0004006 | SO2024102201-SO2024102201-012安装板发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1964 |  | 13 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -12
29 | 1967 | 7 | P112407-0004007 | SO2024102201-SO2024102201-005支架发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1966 |  | 13 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -5
29 | 1968 | 8 | P112407-0004008 | SO2024102201-SO2024102201-006板发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1967 |  | 13 | DP |  |  | PROD_LINE | 15 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -6
29 | 1969 | 9 | P112407-0004009 | SO2024102201-SO2024102201-007鞍式支座发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1968 |  | 13 | DP |  |  | PROD_LINE | 19 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -7
29 | 1970 | 10 | P112407-0004010 | SO2024102201-SO2024102201-003油分离器发运活动 | TRANS | 2024-11-07 | 2024-11-20 |  |  | 1969 |  | 13 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-11-07 13:27 | admin | admin | 2024-11-07 13:27 | NEW | N | Y | -3
39 | 1992 | 1 | P122406-0003001 | 9673-9673-50LA-KZ,PLC控制柜发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  |  |  | -2837 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -20
39 | 1993 | 2 | P122406-0003002 | 9673-9673-40LA-KZ,PLC控制柜发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1992 |  | -2837 | DP |  |  | PROD_LINE | 33 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -19
39 | 1994 | 3 | P122406-0003003 | 9673-9673-120-,40-GLQ15油过滤器DN15直通对焊碳钢75微米2.5MPa发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1992 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -27
39 | 1995 | 4 | P122406-0003004 | 9673-9673-100N窄面垫片,480X440X4.5,0222发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1994 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -25
39 | 1996 | 5 | P122406-0003005 | 9673-9673-150HY21F-25P三位一体阀DN15阀体不锈钢2.5MPa进口卡套出口卡套氨氟、发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1995 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -30
39 | 1997 | 6 | P122406-0003006 | 9673-9673-130-,40-GLQ20油过滤器DN20直通对焊碳钢75微米2.5MPa发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1996 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -28
39 | 1998 | 7 | P122406-0003007 | 9673-9673-60LA200-2.2,自动柜,变频,有主机、油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1997 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -21
39 | 1999 | 8 | P122406-0003008 | 9673-9673-80LA400-4,自动柜,变频,有油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1998 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -23
39 | 2000 | 9 | P122406-0003009 | 9673-9673-70LA400-4,自动柜,变频,有油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1999 |  | -2837 | DP |  |  | PROD_LINE | 17 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -22
39 | 2001 | 10 | P122406-0003010 | 9673-9673-110垫片,299X281X4.5,0220发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2000 |  | -2837 | DP |  |  | PROD_LINE | 29 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -26
39 | 2002 | 11 | P122406-0003011 | 9673-9673-160YB垫片230X206X3,材料QF3710 t=3发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2001 |  | -2837 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -31
39 | 2003 | 12 | P122406-0003012 | 9673-9673-140YB垫片230X206X3,材料QF3710 t=3发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2002 |  | -2837 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-12-06 16:23 | admin | admin | 2024-12-06 16:23 | NEW | N | Y | -29
39 | 2025 | 13 | P122406-0003013 | 9673-9673-50LA-KZ,PLC控制柜发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2003 |  | -2837 | DP |  |  | PROD_LINE | 15 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -20
39 | 2026 | 14 | P122406-0003014 | 9673-9673-40LA-KZ,PLC控制柜发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2025 |  | -2837 | DP |  |  | PROD_LINE | 15 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -19
39 | 2027 | 15 | P122406-0003015 | 9673-9673-120-,40-GLQ15油过滤器DN15直通对焊碳钢75微米2.5MPa发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2026 |  | -2837 | DP |  |  | PROD_LINE | 19 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -27
39 | 2028 | 16 | P122406-0003016 | 9673-9673-100N窄面垫片,480X440X4.5,0222发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2027 |  | -2837 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -25
39 | 2029 | 17 | P122406-0003017 | 9673-9673-150HY21F-25P三位一体阀DN15阀体不锈钢2.5MPa进口卡套出口卡套氨氟、发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2028 |  | -2837 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -30
39 | 2030 | 18 | P122406-0003018 | 9673-9673-130-,40-GLQ20油过滤器DN20直通对焊碳钢75微米2.5MPa发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2029 |  | -2837 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -28
39 | 2031 | 19 | P122406-0003019 | 9673-9673-60LA200-2.2,自动柜,变频,有主机、油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 1993 |  | -2837 | DP |  |  | PROD_LINE | 15 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -21
39 | 2032 | 20 | P122406-0003020 | 9673-9673-80LA400-4,自动柜,变频,有油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2031 |  | -2837 | DP |  |  | PROD_LINE | 16 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -23
39 | 2033 | 21 | P122406-0003021 | 9673-9673-70LA400-4,自动柜,变频,有油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2032 |  | -2837 | DP |  |  | PROD_LINE | 17 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -22
39 | 2034 | 22 | P122406-0003022 | 9673-9673-110垫片,299X281X4.5,0220发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2033 |  | -2837 | DP |  |  | PROD_LINE | 17 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -26
39 | 2035 | 23 | P122406-0003023 | 9673-9673-160YB垫片230X206X3,材料QF3710 t=3发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2034 |  | -2837 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -31
39 | 2036 | 24 | P122406-0003024 | 9673-9673-140YB垫片230X206X3,材料QF3710 t=3发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2035 |  | -2837 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-12-10 10:01 | admin | admin | 2024-12-10 10:01 | NEW | N | Y | -29
40 | 2037 | 1 | P122410-0001001 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -52
40 | 2038 | 2 | P122410-0001002 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -40
40 | 2039 | 3 | P122410-0001003 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -47
40 | 2040 | 4 | P122410-0001004 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -48
40 | 2041 | 5 | P122410-0001005 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -53
40 | 2042 | 6 | P122410-0001006 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -49
40 | 2043 | 7 | P122410-0001007 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -42
40 | 2044 | 8 | P122410-0001008 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -41
40 | 2045 | 9 | P122410-0001009 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -39
40 | 2046 | 10 | P122410-0001010 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -33
40 | 2047 | 11 | P122410-0001011 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -34
40 | 2048 | 12 | P122410-0001012 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -35
40 | 2049 | 13 | P122410-0001013 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -36
40 | 2050 | 14 | P122410-0001014 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -37
40 | 2051 | 15 | P122410-0001015 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -38
40 | 2052 | 16 | P122410-0001016 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -43
40 | 2053 | 17 | P122410-0001017 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -44
40 | 2054 | 18 | P122410-0001018 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -45
40 | 2055 | 19 | P122410-0001019 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -46
40 | 2056 | 20 | P122410-0001020 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -50
40 | 2057 | 21 | P122410-0001021 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:12 | admin | admin | 2024-12-10 10:12 | NEW | N | Y | -51
40 | 2058 | 22 | P122410-0001022 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -52
40 | 2059 | 23 | P122410-0001023 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -40
40 | 2060 | 24 | P122410-0001024 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -47
40 | 2061 | 25 | P122410-0001025 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -48
40 | 2062 | 26 | P122410-0001026 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -53
40 | 2063 | 27 | P122410-0001027 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -49
40 | 2064 | 28 | P122410-0001028 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -42
40 | 2065 | 29 | P122410-0001029 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -41
40 | 2066 | 30 | P122410-0001030 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -39
40 | 2067 | 31 | P122410-0001031 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -33
40 | 2068 | 32 | P122410-0001032 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -34
40 | 2069 | 33 | P122410-0001033 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -35
40 | 2070 | 34 | P122410-0001034 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -36
40 | 2071 | 35 | P122410-0001035 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -37
40 | 2072 | 36 | P122410-0001036 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -38
40 | 2073 | 37 | P122410-0001037 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -43
40 | 2074 | 38 | P122410-0001038 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -44
40 | 2075 | 39 | P122410-0001039 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -45
40 | 2076 | 40 | P122410-0001040 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -46
40 | 2077 | 41 | P122410-0001041 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -50
40 | 2078 | 42 | P122410-0001042 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:33 | admin | admin | 2024-12-10 10:33 | NEW | N | Y | -51
40 | 2079 | 43 | P122410-0001043 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -52
40 | 2080 | 44 | P122410-0001044 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -40
40 | 2081 | 45 | P122410-0001045 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -47
40 | 2082 | 46 | P122410-0001046 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -48
40 | 2083 | 47 | P122410-0001047 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -53
40 | 2084 | 48 | P122410-0001048 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -49
40 | 2085 | 49 | P122410-0001049 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -42
40 | 2086 | 50 | P122410-0001050 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -41
40 | 2087 | 51 | P122410-0001051 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -39
40 | 2088 | 52 | P122410-0001052 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -33
40 | 2089 | 53 | P122410-0001053 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -34
40 | 2090 | 54 | P122410-0001054 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -35
40 | 2091 | 55 | P122410-0001055 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -36
40 | 2092 | 56 | P122410-0001056 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -37
40 | 2093 | 57 | P122410-0001057 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -38
40 | 2094 | 58 | P122410-0001058 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -43
40 | 2095 | 59 | P122410-0001059 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -44
40 | 2096 | 60 | P122410-0001060 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -45
40 | 2097 | 61 | P122410-0001061 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -46
40 | 2098 | 62 | P122410-0001062 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -50
40 | 2099 | 63 | P122410-0001063 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 10:36 | admin | admin | 2024-12-10 10:36 | NEW | N | Y | -51
42 | 2100 | 1 | P122410-0003001 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -52
42 | 2101 | 2 | P122410-0003002 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -40
42 | 2102 | 3 | P122410-0003003 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -47
42 | 2103 | 4 | P122410-0003004 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -48
42 | 2104 | 5 | P122410-0003005 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -53
42 | 2105 | 6 | P122410-0003006 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -49
42 | 2106 | 7 | P122410-0003007 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -42
42 | 2107 | 8 | P122410-0003008 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -41
42 | 2108 | 9 | P122410-0003009 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -39
42 | 2109 | 10 | P122410-0003010 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -33
42 | 2110 | 11 | P122410-0003011 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -34
42 | 2111 | 12 | P122410-0003012 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -35
42 | 2112 | 13 | P122410-0003013 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -36
42 | 2113 | 14 | P122410-0003014 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -37
42 | 2114 | 15 | P122410-0003015 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -38
42 | 2115 | 16 | P122410-0003016 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -43
42 | 2116 | 17 | P122410-0003017 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -44
42 | 2117 | 18 | P122410-0003018 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -45
42 | 2118 | 19 | P122410-0003019 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -46
42 | 2119 | 20 | P122410-0003020 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -50
42 | 2120 | 21 | P122410-0003021 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-10 11:34 | admin | admin | 2024-12-10 11:34 | NEW | N | Y | -51
42 | 2121 | 22 | P122410-0003022 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -52
42 | 2122 | 23 | P122410-0003023 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -40
42 | 2123 | 24 | P122410-0003024 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -47
42 | 2124 | 25 | P122410-0003025 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -48
42 | 2125 | 26 | P122410-0003026 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -53
42 | 2126 | 27 | P122410-0003027 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -49
42 | 2127 | 28 | P122410-0003028 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -42
42 | 2128 | 29 | P122410-0003029 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -41
42 | 2129 | 30 | P122410-0003030 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -39
42 | 2130 | 31 | P122410-0003031 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -33
42 | 2131 | 32 | P122410-0003032 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -34
42 | 2132 | 33 | P122410-0003033 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -35
42 | 2133 | 34 | P122410-0003034 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -36
42 | 2134 | 35 | P122410-0003035 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -37
42 | 2135 | 36 | P122410-0003036 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -38
42 | 2136 | 37 | P122410-0003037 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -43
42 | 2137 | 38 | P122410-0003038 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -44
42 | 2138 | 39 | P122410-0003039 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -45
42 | 2139 | 40 | P122410-0003040 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -46
42 | 2140 | 41 | P122410-0003041 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -50
42 | 2141 | 42 | P122410-0003042 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 09:51 | admin | admin | 2024-12-17 09:51 | NEW | N | Y | -51
42 | 2144 | 43 | P122410-0003043 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -52
42 | 2145 | 44 | P122410-0003044 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -40
42 | 2146 | 45 | P122410-0003045 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -47
42 | 2147 | 46 | P122410-0003046 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -48
42 | 2148 | 47 | P122410-0003047 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -53
42 | 2149 | 48 | P122410-0003048 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -49
42 | 2150 | 49 | P122410-0003049 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -42
42 | 2151 | 50 | P122410-0003050 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -41
42 | 2152 | 51 | P122410-0003051 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -39
42 | 2153 | 52 | P122410-0003052 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -33
42 | 2154 | 53 | P122410-0003053 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -34
42 | 2155 | 54 | P122410-0003054 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -35
42 | 2156 | 55 | P122410-0003055 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -36
42 | 2157 | 56 | P122410-0003056 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -37
42 | 2158 | 57 | P122410-0003057 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -38
42 | 2159 | 58 | P122410-0003058 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -43
42 | 2160 | 59 | P122410-0003059 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -44
42 | 2161 | 60 | P122410-0003060 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -45
42 | 2162 | 61 | P122410-0003061 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -46
42 | 2163 | 62 | P122410-0003062 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -50
42 | 2164 | 63 | P122410-0003063 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-10 | 2019-04-05 |  |  |  |  | -2076 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:19 | admin | admin | 2024-12-17 11:19 | NEW | N | Y | -51
44 | 2165 | 1 | P122417-0001001 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -52
44 | 2166 | 2 | P122417-0001002 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -40
44 | 2167 | 3 | P122417-0001003 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -47
44 | 2168 | 4 | P122417-0001004 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -48
44 | 2169 | 5 | P122417-0001005 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -53
44 | 2170 | 6 | P122417-0001006 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -49
44 | 2171 | 7 | P122417-0001007 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -42
44 | 2172 | 8 | P122417-0001008 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -41
44 | 2173 | 9 | P122417-0001009 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -39
44 | 2174 | 10 | P122417-0001010 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -33
44 | 2175 | 11 | P122417-0001011 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -34
44 | 2176 | 12 | P122417-0001012 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -35
44 | 2177 | 13 | P122417-0001013 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -36
44 | 2178 | 14 | P122417-0001014 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -37
44 | 2179 | 15 | P122417-0001015 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -38
44 | 2180 | 16 | P122417-0001016 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -43
44 | 2181 | 17 | P122417-0001017 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -44
44 | 2182 | 18 | P122417-0001018 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -45
44 | 2183 | 19 | P122417-0001019 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -46
44 | 2184 | 20 | P122417-0001020 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -50
44 | 2185 | 21 | P122417-0001021 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 11:29 | admin | admin | 2024-12-17 11:29 | NEW | N | Y | -51
46 | 2186 | 1 | P122417-0003001 | 21240-21240-210GB/T6177.1,螺母M6-A2-70,-,不锈钢发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  |  |  | -2083 | DP |  |  | PROD_LINE | 22 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -52
46 | 2187 | 2 | P122417-0003002 | 21240-21240-90-,SBQ61F-25P直通球阀DN20,170,CF8, -50～150℃,制发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2186 |  | -2083 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -40
46 | 2188 | 3 | P122417-0003003 | 21240-21240-160GB/T1226径向压力表100-0～4MPa-1.6,不锈钢,耐震是,直接发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2187 |  | -2083 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -47
46 | 2189 | 4 | P122417-0003004 | 21240-21240-170YT01L01010201垫片DN6,PTFE,尺寸18X11X1.5发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2188 |  | -2083 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -48
46 | 2190 | 5 | P122417-0003005 | 21240-21240-220GB/T6175,螺母M16,氧化处理,30CrMoA发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2188 |  | -2083 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -53
46 | 2191 | 6 | P122417-0003006 | 21240-21240-180BTA-42B25C3安全阀DN32 2.2MPa背压-阀体LCB制冷剂、工业气发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2189 |  | -2083 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -49
46 | 2192 | 7 | P122417-0003007 | 21240-21240-110042H2104,AKVA20-4电子膨胀阀,1-1/2X1-1/2in对焊发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2191 |  | -2083 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -42
46 | 2193 | 8 | P122417-0003008 | 21240-21240-100027F3061,PMFL125,液位调节阀,法兰连接发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2192 |  | -2083 | DP |  |  | PROD_LINE | 17 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -41
46 | 2194 | 9 | P122417-0003009 | 21240-21240-80过滤网组件,245X8X552,57X5发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2193 |  | -2083 | DP |  |  | PROD_LINE | 29 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -39
46 | 2195 | 10 | P122417-0003010 | 21240-21240-20012306010005,膨胀撬块,公称容积10发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2194 |  | -2083 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -33
46 | 2196 | 11 | P122417-0003011 | 21240-21240-30GBT16630,冷冻机油LT-32发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2194 |  | -2083 | DP |  |  | PROD_LINE | 14 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -34
46 | 2197 | 12 | P122417-0003012 | 21240-21240-40GB/T16630,冷冻油M-K4001(A)发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2196 |  | -2083 | DP |  |  | PROD_LINE | 15 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -35
46 | 2198 | 13 | P122417-0003013 | 21240-21240-500800/58B//BP/489F,机械密封80,散装发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2197 |  | -2083 | DP |  |  | PROD_LINE | 15 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -36
46 | 2199 | 14 | P122417-0003014 | 21240-21240-600200/58U//BO/XR1S1,机械密封20,散装发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2198 |  | -2083 | DP |  |  | PROD_LINE | 19 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -37
46 | 2200 | 15 | P122417-0003015 | 21240-21240-70过滤网组件,377X10X897,273X10发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2199 |  | -2083 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -38
46 | 2201 | 16 | P122417-0003016 | 21240-21240-120"O"型圈85.32X3.53,FPM80，ZZB90发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2200 |  | -2083 | DP |  |  | PROD_LINE | 18 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -43
46 | 2202 | 17 | P122417-0003017 | 21240-21240-130OXMFQ,"O"型圈94.3X5.7,FPM80发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2201 |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -44
46 | 2203 | 18 | P122417-0003018 | 21240-21240-140OXMFQ,"O"型圈28.17X3.53,FPM80发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2202 |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -45
46 | 2204 | 19 | P122417-0003019 | 21240-21240-150OXMFQ,"O"型圈20.29X2.62,FPM80发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2203 |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -46
46 | 2205 | 20 | P122417-0003020 | 21240-21240-190HG/T20592,法兰SO32B-25M,20ⅡA发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2204 |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -50
46 | 2206 | 21 | P122417-0003021 | 21240-21240-200HG/T20610,缠绕垫B32,0222发运活动 | TRANS | 2024-12-17 | 2019-04-05 |  |  | 2205 |  | -2083 | DP |  |  | PROD_LINE | 35 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -51
39 | 2207 | 25 | P122406-0003027 | 9673-9673-50LA-KZ,PLC控制柜发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2036 |  | -2837 | DP |  |  | PROD_LINE | 21 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -20
39 | 2208 | 26 | P122406-0003028 | 9673-9673-40LA-KZ,PLC控制柜发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2207 |  | -2837 | DP |  |  | PROD_LINE | 22 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -19
39 | 2209 | 27 | P122406-0003029 | 9673-9673-120-,40-GLQ15油过滤器DN15直通对焊碳钢75微米2.5MPa发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2208 |  | -2837 | DP |  |  | PROD_LINE | 23 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -27
39 | 2210 | 28 | P122406-0003030 | 9673-9673-100N窄面垫片,480X440X4.5,0222发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2209 |  | -2837 | DP |  |  | PROD_LINE | 24 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -25
39 | 2211 | 29 | P122406-0003031 | 9673-9673-150HY21F-25P三位一体阀DN15阀体不锈钢2.5MPa进口卡套出口卡套氨氟、发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2210 |  | -2837 | DP |  |  | PROD_LINE | 25 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -30
39 | 2212 | 30 | P122406-0003032 | 9673-9673-130-,40-GLQ20油过滤器DN20直通对焊碳钢75微米2.5MPa发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2211 |  | -2837 | DP |  |  | PROD_LINE | 25 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -28
39 | 2213 | 31 | P122406-0003033 | 9673-9673-60LA200-2.2,自动柜,变频,有主机、油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2212 |  | -2837 | DP |  |  | PROD_LINE | 27 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -21
39 | 2214 | 32 | P122406-0003034 | 9673-9673-80LA400-4,自动柜,变频,有油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2030 |  | -2837 | DP |  |  | PROD_LINE | 27 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -23
39 | 2215 | 33 | P122406-0003035 | 9673-9673-70LA400-4,自动柜,变频,有油分加热发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2214 |  | -2837 | DP |  |  | PROD_LINE | 28 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -22
39 | 2216 | 34 | P122406-0003036 | 9673-9673-110垫片,299X281X4.5,0220发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2215 |  | -2837 | DP |  |  | PROD_LINE | 29 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -26
39 | 2217 | 35 | P122406-0003037 | 9673-9673-160YB垫片230X206X3,材料QF3710 t=3发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2216 |  | -2837 | DP |  |  | PROD_LINE | 30 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -31
39 | 2218 | 36 | P122406-0003038 | 9673-9673-140YB垫片230X206X3,材料QF3710 t=3发运活动 | TRANS | 2024-12-06 | 2017-03-01 |  |  | 2213 |  | -2837 | DP |  |  | PROD_LINE | 31 | 发运单元 | Y |  | 2024-12-17 15:22 | admin | admin | 2024-12-17 15:22 | NEW | N | Y | -29

## Sheet1
project_id | activity_id | activity_name | activity_type | parent_activity_id | proceeding_activity_id | durance | resource_id | activity_status
10 | 1906 | 合同 | REVIEW |  |  | 5 | 33 | NEW
10 | 1907 | 设计A | DESIGN | 1914 |  | 17 | 28 | NEW
10 | 1908 | 设计A-1 | DESIGN | 1907 | 1906 | 5 | 28 | NEW
10 | 1909 | 设计A-2 | WORKING | 1907 | 1908 | 5 | 28 | NEW
10 | 1910 | 设计A-3 | DESIGN | 1907 | 1909 | 5 | 28 | NEW
10 | 1911 | 设计B | DESIGN | 1914 |  | 12 | 28 | NEW
10 | 1912 | 设计B-1 | DESIGN | 1911 | 1908 | 5 | 28 | NEW
10 | 1913 | 设计B-2 | DESIGN | 1911 | 1909 | 5 | 28 | NEW
10 | 1914 | 设计 | DESIGN |  |  | 23 | 17 | NEW
10 | 1915 | 设计C | DESIGN | 1914 | 1910 | 5 | 29 | NEW
10 | 1916 | 生产 | MAKE |  |  | 12 | 14 | NEW
10 | 1917 | 采购 | PURCHASE |  |  | 9 | 14 | NEW
10 | 1918 | 生产部件 | MAKE | 1916 | 1920 | 5 | 15 | NEW
10 | 1919 | 生产机组 | MAKE | 1916 | 1918 | 5 | 19 | NEW
10 | 1920 | 采购部件 | PURCHASE | 1917 | 1923 | 5 | 18 | NEW
10 | 1921 | 采购其他 | PURCHASE | 1917 | 1923 | 5 | 18 | NEW
10 | 1922 | 发运 | REVIEW |  | 1919 | 5 | 21 | NEW
10 | 1923 | 合同生效 | MAKE |  | 1915 | 1 | 19 | NEW